## Slide 1: Laconia School District Reopening Updated Proposal
Laconia School Board
October 14, 2020

## Slide 2: Overview
Registration Results
Remote Division
  Elementary
  Middle
  High
Phasing-In
  Elementary
  Middle
  High
COVID-19 Planning
Plans for School Closure: Remote
COVID-19 Data and Public Health Guidance
Final Considerations

## Slide 3: Quarter 2 Registration Results
School | QUARTER 1 |  | QUARTER 2 |  | Total Students
 | Face-to-Face | Remote | Face-to-Face | Remote | 
Elm Street | 216 | 59 | 235 | 41 | 275
Pleasant Street | 233 | 38 | 234 | 29 | 263
Woodland Heights | 273 | 72 | 297 | 48 | 345
LMS | 360 | 117 | 393 | 84 | 478
LHS | 475 | 95 | 490 | 80 | 570
TOTALS | 1557 | *381 | 1747 | 292 | 1931
*Initially, 407 students (or 21%) registered for remote. 26 students transferred to face-to-face.

## Slide 4: Quarter 2 Elementary Class Sizes

## Slide 5: Remote Division

## Slide 6: Remote Division: Elementary
Grade Level | Enrollment | Teacher
PreK | 7 | 1 (after school)
K | 15 | 1
1 | 18 | 1
2 | 15 | 1
3 | 21 | 1
4 | 22 | 1
5 | 20 | 1
Totals | 118 | 6 (plus one after school)

## Slide 7: Remote Division: Middle and High
Middle
  2 Staff
  4 Additional Sections
  1 Remote Teacher
  1 Long-term Sub
High
  2 Staff
  4 Additional Sections
  1 Long-Term Sub

## Slide 8: Remote Division: Cost
Level | Funding Source | Quarter 2 | 
 |  | Description | Amount
Elementary | Project Extra! | PreK After School | $3,375.00
 | General Budget (CARES) | 3 remote teachers | $20,250.00
MIddle | Project Extra! | 3 additional sections | $6,210.00
 | General Budget (CARES) | 1 additional section | $2,070.00
 |  | 1 remote teacher | $6,750.00
 |  | Long term Math sub | $9,945.00
High | General Budget (CARES) | 4 additional sections | $8,280.00
 |  | 1 long-term sub | $9,945.00
TOTALS |  |  | $66,825.00

## Slide 9: Phasing-In Plan

## Slide 10: Huot Technical Center
Opened to all students in the AREA and Newfound on October 5
Attendance has been over 75 percent
Transportation
Instruction
Franklin and Belmont - remote beginning October 13 (contact tracing)

## Slide 11: Phasing In: Elementary
October 19: Kindergarten
October 26: Grade 1
November 2: Grade 2
November 9: Grade 3
November 16: Grade 4 and 5 (note change)
Remote students coming back will phase in on November 16th.

## Slide 12: Phasing In: LMS and LHS
LMS
November 5: Grade 6
November 9: Grade 7
November 12: Grade 8
LHS
October 14: Grade 12
October 14-November 2: Grade 11 and 10
November 2: Grade 9

## Slide 13: Logistical Considerations
Transportation
Snacks
Staffing
Quarantining scenarios
Mask and masks breaks
Some classes - size
Day cleaning
Facility use
Other

## Slide 14: Critical Consideration
This “phasing in” plan is subject to change at anytime based on COVID - 19 conditions

## Slide 15: COVID-19 Planning

## Slide 16: COVID-19 Response Scenarios and Plans
New or unexplained symptoms
Close contact - confirmed case (cannot test out)
Close contact - suspected case
Travel outside New England (cannot test out)
Reported confirmed or suspected case to the school
New or unexplained symptoms in the school day
Investigation - suspected or confirmed case on school grounds

## Slide 17: 5 Steps: Positive COVID-19 Tests
Case interview
Identification of close contacts
  10 minutes
  Less than 6 feet
Isolation for people with COVID-19
Quarantine of close contacts (cannot test out)
Return to school
Quarantine
Student (Google Classroom)
Staff (Human Resources)

## Slide 18: Plans for School Closure: Remote

## Slide 19: Remote Learning Scenarios
Short term
  COVID-19: Group, building, or district
    Contact tracing
    Staffing
  Increase structure
  Snow days
    First two: Staff training, no school for students
    After 2: Remote days
Long term considerations
  Vacations
  Flex day

## Slide 20: Sample Remote Elementary Schedule
8:00-8:30 Morning Meeting
8:30-9:30 Literacy
9:30-10:30 Math
10:30-11:30 Social Studies/Science
11:30-12:00 Lunch
12:00-12:40 Exploratory
12:40-3:00 Team meetings / Teacher Work Time / Support for Students (times and days will vary)

## Slide 21: Sample Remote Middle School Schedule
8:00-8:45 Period 1 (Grade 8 Exploratory) / Grade 8 Teacher Plan
9:00-9:45 Period 2 Exploratory Teacher Plan
10:00-10:45 Period 3 (Grade 6 Exploratory) / Grade 6 Teacher Plan
11:00-11:45 Period 4
11:45-12:15 LUNCH
12:15-1:00 Period 5 (Grade 7 Exploratory) / Grade 7 Teacher Plan
1:00-3:00 Office Hours, Small Group Instruction & Meetings

## Slide 22: Sample Remote High School Schedule
Block 1 8:00 - 8:50
Block 2 9:10 - 10:00
SSB 10:20 - 11:00
Lunch 11:00 - 11:30
Block 3 11:40 - 12:30
Block 4 12:50 - 1:40
Teacher Office Hours 1:50 - 3:00

## Slide 23: COVID-19 Data and Public Health Guidance

## Slide 24
Laconia: 5 current cases as of October 12, 2020
(Source, NH-DHHS)

## Slide 26: “Considerations for Transitioning Between School Instructional Models Based on Level of Community COVID-19 Transmission and Impact on Local Schools” (September 1, 2020)
See this document from the NH Division of Public Health Services, Bureau of Infectious Disease Control and the next three slides.

## Slide 27: Community Transmission Guidance
Criteria | Level of Community Transmission |  | 
 | Minimal | Moderate | Substantial
COVID-19 PCR test positivity as a 7 day average | < 5% 0.4% in Belknap County (down from 0.5%) | 5 – 10% | >10%
Number of new infections per 100,000 population over prior 14 days | < 50 | 50-100 50.8 in Belknap County from Sept. 28 to Oct 11 - Population 61,303 | >100
Number of new hospitalizations per 100,000 people over the prior 14 days | < 10 1.6 in Belknap County (first new one in 67 days as of October 10) | 10-20 | >20

## Slide 28: Determining Level of COVID-19 School Impact
Criteria | Level of School Impact |  | 
 | Low | Medium | High
Transmission in the school facility | Zero or sporadic cases with no evidence of transmission within the school setting | One cluster* in the school | Two or more unrelated clusters* in the school with onset (based on source case symptom onset dates) within 14 days of each other
Student absenteeism due to illness | <15% Rates in Laconia schools range between 6-9% | 15-30% | >30%
Staff capacity to conduct classes and school operations † | Normal | Strainted | Critical
* A cluster is defined as 3 or more individuals confirmed with COVID-19 who are part of a related group of individuals (e.g., classroom) who had the potential to transmit infection to each other through close contact.
† This subjective assessment should factor in a school’s ability to maintain adequate staff for facility operations, transportation, teaching, and administrative functions.

## Slide 29: Decision Matrix for Transitioning Between Methods of Instruction
See the Community Level Transmission Metrics for Belknap County at NH-DHHS
As of October 13, 2020

## Slide 30: Final Considerations
Current mitigation strategies continue to be important:
  Screening
  Physical distancing
  Masks
Communication with Dr. Ben Chan
This “phasing in” plan is subject to change at anytime based on COVID - 19 conditions